## Sheet1
Establishing Energy Efficiency in Building (other than housing)
Process | Responsible | Kyoto Protocol | Bi-national | Department | South African | AAAMSA inc | Council | SC5120.61 | Department | Inter- | Cabinet | Parliament
or | Government | World Bank | Commission | of Minerals | Bureau of | TIASA - | Scientific & | Construction | Trade & | Departmental | Committee
task | Department | Danida & | between USA | and Energy | Standards | Thermal | Industrial | Standards | Industry | Energy
number | or Organisation | USAID | & South Africa |  |  | Insulation | Research/ | Thermal perform |  | Cluster
[6 empty] | Association | Agrement SA | Energy usage
| Description of process/task |  |  |  |  | SAGGA - |  | Built Environ
SA Glass &
Glasing Assoc.
1 | South Africa signs the Kyoto protocol
2 | Department of Minerals & Energy
issues white paper on EE
3 | Gore Mbeki cooperation on Energy
4 | SAEDES Joint US/SA working group formed
5 | SC5120.61K is mandated to ammend the
Building Regulations
6 | Papers presented on potential for EE in
Buildings in SA
7 | TIASA proposes U-values for all buildings
8 | TIASA proposals for revision of National
Building Regulations is rejected
for not being performance based
9 | Sodelunde&Shutte report presents the housing EE
way forward as being via SANS document
10 | SAEDES Joint US/SA working group finalises
Guideline
11 | SANS 204 project is initiated by DME
12 | SANS 204 project is upgraded to a sub-committee
of TC61 by StanSA & becomes SC5120.61
13 | SANS 204 project is supported by CaBEERE
who pledge funding for supporting research
14 | StanSA R&D agree to manage research project
15 | Research Group is convened by StanSA R&D
16 | Research Outputs are collated and tabulated
for incorporation into WD204
17 | Further research to cover gaps in
SANS 283 and 204 projects
Climatic zone definition Daylighting and glass research
18 | SANS SC5120.61K formally adopts CSIR draft as WD204
WD stage has no time limits
Wide consultantion at this stage is required
Research gaps to be identified
18.1 | WD document becomes a CD for comment period - 3 weeks
18.2 | SC5120.61K reviews document - Concensus required 50%
18.3 | Circulates for Technical Review in SABS - 2 month
19.1 | TIASA issues Code of practice
19.2 | Research gaps funded, or SAEDES used
19.3 | Glass industry & THRIP fund research into
daylighting, window sizing, Trombe Wall
20 | Committee draft editing - DSS stage - 60 days
DSS 204 for public comment
No new technical comment from SC at this stage
21 | TIASA promotes Code of practice to SANS 10-400
committee referes for review by SC5120.61K
22 | DME Impact assessment to DTI for Regulatory review
23 | SABS impact assessment group review begins
24 | Code of practice for implementation of Energy
Efficiency in buildings accepted by TC61
25 | SABS regulatory review begins
26 | SABS regulatory review recommends
27 | SC 5120.61K recommends ammendment SANS10-400 to TC61
SC 5120.61K votes to finalise and accept SANS 204
28 | DME imact assessment finalised/ recommendations
passed to DG
DG for M&E intitiated legislative process
29 | Minister of Minerals & Energy draws up ammendments
to Energy legistation enabling SANS 204
and aspects of 283
30 | TIASA develops Handbook & code of practice for EE
SAIRAC develops Guideline?
31 | Cabinet approval for EE Act sought
32 | Parliament ammends Energy act and
to Act 103 National Buildings & Standards Act
33 | TC61 approves ammendment of SANS10-400 for EE
and LCH aspects
34 | Department of Trade & Industries amends NBR
35 | Implementation of EE in Building commences
36 | DME workshops EE in Building
SAEDES Guideline
for EE in
Commercial buildings
USAid
supports EE
by funding
research &
study trips
TIASA
code of practice statement on EE in building
developed
SANS 204
Research
Projects
incorporates
necessary
EE research
New draft
of SANS
10-400 to be completed in 2004
TIASA
proposal for
U-values
in NBR
Revision
of NBR
drafting prepared
by TIASA
Energy white
paper signals action for department
on EE
National
Building
Regulations
Ammend-
ment SANS 10-400
Draft SANS 10-400 incorporate Code of practice
for deemed
to satisfy
EE in buildings
SANS 10-400
National
Building
Regulations
revised for EE
& LCH aspects
Energy Act ammended by DME
Energy
cluster draft
legislation
Cabinet
approval
obtained
for new EE prov
Act
Code of practice
for EE implementation
in building
Guidelines&
Handbooks
Published
Seminars and road-shows
training courses
Act 103
National
Buildings Regulation and
Standards
Energy Act
Ammended
Bills pass
through
Parliament
Kyoto
Protocol
Protocol
between
DME (SA)&
DoE (USA)
on EE
CSIR Working
Group
Mandated
to draft SANS 204
SANS 204
document
draft
started
WD 204
Project draft
tabled
Eskom/SAGGA
Research into
Glass and Day-lighting finalised
Ammendment to National Building and Standards
Act 103
TIASA code
of practice
finalised and harmonised
with DSS204
DTI
Impact assessment
DTI
Regulatory
review
draft
DME evaluation
of SANS 204
document
DME positive evaluation
with DG
endorsement
SANS204 Facititation project
Extention
SANS 204
Research Extention
DSS 204
process is conducted
CD 204
Committee
Draft for Tech review
SC5120.61K
review comments collated
SAEDES
Guideline
content
SANS 204
process is finalised